## Short Report
MAJOR PROJECTS STATUS REPORT
UPDATED: November 19, 2025
Project Number | Name | Campus | PM | Current Phase | Architect | Contractor | Project Budget | GMP/Bid Budget | Construction Start Date | Comments
BT-640 | 2026 Student Campus Housing | Boca | IM | Construction | HKS | Balfour Beatty | 125723372 | 101000000 | 2025-01-25 | The project remains on schedule. Precast panel installation is in progress, and interior framing is ongoing. All MEP rough-in work is underway. Roofing activities will begin this week to prepare for roof installation. CP underground piping inside the building has been completed.
BT-652 | Henderson University School Phase II | Boca | IM | Close Out | Harvard Jolly | Moss Construction | 33225240 | 27000000 | 2025-01-24 | Project complete - Punchlist Walkthrough scheduled 12/10/25.
BT-686 | Student Union Expansion | Boca | IM | Design | DLR | Balfour Beatty | 25159508.46 | 20100000 | 2025-01-26 | In Design/Development Phase. Reviewing DD phase on 12/4/25.
BT-690 | Wallach Institute for Holocaust & Jewish Studies | Boca | IM | Pre-Construction | SRS Architects | Gilbane | 18828893 | 16000000 | 2025-08-25 | Foundation work and underground civil infrastructure are currently in progress.
BT- 636 | Health Professions Training & Research Facility | Boca | AD | Planning | TBD | TBD | 10000000 |  | TBD | In Programming Phase.
BT - 602 | Arena Expansion | Boca | AD | Programming | TBD | TBD | TBD | TBD | TBD | Reviewing Funding.